## Sheet1
PERT analysis
Task | Duration | Optimistic | Expected | Pessimistic | Start | Finish
Preliminary Research | 1.5 wks | 7 days | 7 days | 10 days | 2003-01-20 08:00 | 2003-01-29 12:00
Setting up MSX and test | 1.5 wks | 7 days | 7 days | 10 days | 2003-01-27 08:00 | 2003-02-05 12:00
Preliminary Schematic Design | 1.83 wks | 1 wk | 2 wks | 2 wks | 2003-01-27 08:00 | 2003-02-07 09:20
First prototype testing - test interface circuitry | 3.17 days | 3 days | 3 days | 4 days | 2003-02-03 08:00 | 2003-02-06 09:20
Redesign and check schematic | 1.13 wks | 1 wk | 1 wk | 9 days | 2003-02-06 09:20 | 2003-02-13 15:40
PCB layout | 1.07 wks | 4 days | 1 wk | 8 days | 2003-02-13 15:40 | 2003-02-20 09:20
Send out for PCB fabrication | 2.17 wks | 2 wks | 2 wks | 3 wks | 2003-02-20 09:20 | 2003-03-06 17:00
Send out for board assembly | 2.17 wks | 2 wks | 2 wks | 3 wks | 2003-03-07 08:00 | 2003-03-21 15:40
Test MSX with card plugged-in | 2.17 days | 2 days | 2 days | 3 days | 2003-03-21 15:40 | 2003-03-25 17:00
Driver development | 2.17 wks | 2 wks | 2 wks | 15 days | 2003-03-26 08:00 | 2003-04-09 15:40
Final validation (check for stability and usability) | 3.17 days | 2 days | 3 days | 5 days | 2003-04-09 15:40 | 2003-04-14 17:00